## Overview
Core Platform - Control Room
A generic, multi-product backend platform (Go services + Next.js admin + Flutter mobile + Terraform/Helm/Docker infra), built phase-by-phase against a 30-phase roadmap.
At a glance
Phases complete | 24 / 30 | 80%
Backend services | 3 | core-api, realtime-gateway, worker
Shared Go packages | 1 | packages/go/platformkit
Domain modules (core-api) | 24 | one per completed phase
Live HTTP endpoints | 142 | see 'API Endpoints' sheet
DB migrations | 22 | data/migrations/0001-0022
Real infra dependencies | 10 | Postgres, Valkey, Keycloak, OpenFGA, MinIO, OpenSearch, Temporal, Kafka/Redpanda, Ollama, OTel
Commits so far | 32 | see git log
How to read this workbook
• Roadmap - all 30 phases, one row each, status + what it delivers.
• Todo Checklist - granular task list (completed sub-items and still-to-do sub-items) so progress is trackable at a finer grain than 'phase done or not'.
• Modules - every backend/core-api/internal module: what it owns, its storage, its access rule.
• API Endpoints - every live HTTP route across all three services, with auth level.
• How To Test - copy-paste steps to bring the stack up locally and exercise it for real (mint a token, call endpoints, open a WebSocket).
• Infra & Credentials - every local service, its port, and its local-only credentials.

## Roadmap
Phase | Status | Name | What it delivers | Commit
1 | Done | Platform Foundation | config/logging/errors/health/correlation IDs/OTel/graceful shutdown - the shared platformkit every later phase builds on. | 9b9a65a
2 | Done | Application Registry | First real domain module: Application CRUD, cursor pagination, application.created/updated events. | 65a937d
3 | Done | Identity | Provider abstraction over Keycloak (JWT validation + Admin API), platform-owned IdentityID/UserID, identities linkage table. | 987f0cf
4 | Done | Users | Platform person/account, separate from Identity. Soft-delete lifecycle, auto-provision on first login. | 3f0289e
5 | Done | Devices / Sessions | Per-user device tracking, push-token storage, revoke/reactivate, raw tokens never exposed in responses. | 0762cfa
6 | Done | Authorization / Access | authz.Service.Can(subject, action, resource) - RBAC (Postgres) + fine-grained ReBAC (OpenFGA), the one entry point every module uses. | 892db7b
7 | Done | Tenants / Organizations | Tenant + Membership (owner/admin/member), scoped to an Application. Tenant-role checks answered from Membership data, not OpenFGA. | 9040905
8 | Done | Relationships / Social Graph | Generic RelationshipType/Relationship/Status graph: request/accept/decline/remove/block, no fixed 'friend/follower' semantics. | 542604c
9 | Done | Groups / Circles | Generic Group/GroupMember primitive (friend circles, teams, guilds - same shape), free-form product-defined member roles. | 02b5767
10 | Done | Realtime Platform | New realtime-gateway service: hand-rolled WebSocket (RFC6455), Redis-fanned pub/sub for cross-replica delivery, TTL-based presence. | 1eda4b3
11 | Done | Messaging | Conversation/Message/Delivery/ReadState/Reaction/Attachment, realtime delivery via a new shared rtbus package, durable storage in Postgres. | a199c4c
12 | Done | Notification Platform | Notification/Template/Preference/Delivery across push/email/sms/in_app/realtime; only push is genuinely provider-tested locally (real device-token check). | 95b8e05
13 | Done | File / Media Platform | Presigned upload/download against real MinIO/S3, real MD5 checksum verification, ownership/permissions/retention/purge. | 9a39606
14 | Done | Search Platform | SearchDocument/SearchProvider over OpenSearch; event-driven indexing via a new worker service polling the outbox. | 6a4eafd
15 | Done | Background Jobs | Job/JobStatus/JobAttempt: immediate/scheduled/delayed/recurring/retry/dead-letter, executed by worker, never inline in HTTP handlers. | d9221a4
16 | Done | Workflows | Temporal abstraction (Core Workflow API/SDK) for long-running, multi-step, compensating, scheduled processes - Temporal never exposed directly. | 59dfe77
17 | Done | Feature Flags | Feature/FeatureRule/FeatureEvaluation targeting app/env/user/tenant/platform/country/%/version, deterministic FNV-1a percentage bucketing. | 86925a5
18 | Done | Remote Configuration | Typed key/value store scoped by (AppID, Environment, Key), full change-audit trail, config.updated/deleted events. | 9a0ad7b
19 | Done | Audit | Central Audit Service: actor/action/resource/timestamp/correlation/app/tenant/device/metadata. Immutable by omission AND a DB trigger. | 2629e91
20 | Done | Privacy | Consent (append-only), preferences, retention policy, and cross-module ExportUserData/DeleteUserData via an Exporter/Deleter registry (users/devices/files/audit-export-only). Coordinated by a Temporal workflow core-api runs its own embedded worker for, since worker (separate module) can't reach core-api's internal packages. | 44299b2
21 | Done | Trust & Safety | Mute/Report->ModerationCase (deduplicated)/Suspension/Ban/Appeal - Block reuses Phase 8's relationships, not duplicated. A new requireActive middleware makes Suspension/Ban actually restrict access platform-wide from one place. New shared ratelimit package (Valkey-backed) gates report spam; a critical AbuseSignal auto-opens a case. | 7af4c58
22 | Done | Billing / Entitlements | Entitlement (platform truth, HasEntitlement) kept separate from Payment (provider transaction record). PaymentProvider abstraction + registry; billing/stripe implements Stripe's real webhook HMAC signature scheme, live-validated without a Stripe account via self-signed test payloads. Apple IAP/Google Play deliberately deferred - no sandbox credentials available. | 8fcc87f
23 | Done | Analytics | Generic event envelope, matching the roadmap's own field names verbatim. analytics_events is a landing buffer, never queried for analytics - a new worker pipeline batches unflushed rows as NDJSON into MinIO/S3 (a real data-lake landing pattern). Track is this platform's one open, unauthenticated write endpoint, IP-rate-limited instead of Bearer-gated. | aa207ae
24 | Done | AI Gateway | Provider-neutral interface; real local inference via a new Ollama container (auto-pulled model, no vendor API key) - the one live-testable provider. Model routing, quotas (ratelimit reused again), real token/cost tracking, a genuine audit.Record per call, prompt/version metadata, timeouts, fallback. OpenAI/Anthropic/Google structurally supported, not implemented (no real credentials). | d7324b9
25 | Next up | Admin Portal | The control-plane UI (apps/admin, Next.js) - visibility into apps/users/sessions/devices/roles/tenants/relationships/messages/notifications/files/jobs/flags/config/moderation/audit/health/deployments, always through service APIs, never direct DB queries. | -
26 | Pending | Backstage | Integrate Backstage as the developer portal - every service/module exposes metadata (owner, lifecycle, repo, docs, dependencies, APIs, events, DB ownership, dashboards, runbooks). Backstage becomes the map of the platform. | -
27 | Pending | SDKs | Flutter SDK, TypeScript SDK, Go SDK - auth, token refresh, API calls, errors, pagination, safe retries, realtime connection, correlation IDs, device registration. Future products talk to Core primarily through these. | -
28 | Pending | Observability Completion | Every production component gets structured logs, metrics, traces, health checks, dashboards, alerts. Standard dashboards for API latency, error rate, req/sec, DB connections, Kafka lag, WS connections, Redis latency, notification/job failures. | -
29 | Pending | Platform Control Plane | One view of applications/services/versions/environments/dependencies/deployments/DB ownership/events/API contracts/health/alerts/recent changes - every module discoverable from one place. | -
30 | Pending | AI Development Context | Machine-readable context for AI agents - every module carries README, ownership metadata, dependencies, API contract, event contracts, DB ownership, so an agent (like this one) can safely work on any part of the platform. | -

## Todo Checklist
Phase | Status | Task | Note
1 | Done | Phase 1: Platform Foundation implemented, unit-tested, live-validated, documented, committed
2 | Done | Phase 2: Application Registry implemented, unit-tested, live-validated, documented, committed
3 | Done | Phase 3: Identity implemented, unit-tested, live-validated, documented, committed
4 | Done | Phase 4: Users implemented, unit-tested, live-validated, documented, committed
5 | Done | Phase 5: Devices / Sessions implemented, unit-tested, live-validated, documented, committed
6 | Done | Phase 6: Authorization / Access implemented, unit-tested, live-validated, documented, committed
7 | Done | Phase 7: Tenants / Organizations implemented, unit-tested, live-validated, documented, committed
8 | Done | Phase 8: Relationships / Social Graph implemented, unit-tested, live-validated, documented, committed
9 | Done | Phase 9: Groups / Circles implemented, unit-tested, live-validated, documented, committed
10 | Done | Phase 10: Realtime Platform implemented, unit-tested, live-validated, documented, committed
11 | Done | Phase 11: Messaging implemented, unit-tested, live-validated, documented, committed
12 | Done | Phase 12: Notification Platform implemented, unit-tested, live-validated, documented, committed
13 | Done | Phase 13: File / Media Platform implemented, unit-tested, live-validated, documented, committed
14 | Done | Phase 14: Search Platform implemented, unit-tested, live-validated, documented, committed
15 | Done | Phase 15: Background Jobs implemented, unit-tested, live-validated, documented, committed
16 | Done | Phase 16: Workflows implemented, unit-tested, live-validated, documented, committed
17 | Done | Phase 17: Feature Flags implemented, unit-tested, live-validated, documented, committed
18 | Done | Phase 18: Remote Configuration implemented, unit-tested, live-validated, documented, committed
19 | Done | Phase 19: Audit implemented, unit-tested, live-validated, documented, committed
20 | Done | Phase 20: Privacy implemented, unit-tested, live-validated, documented, committed
21 | Done | Phase 21: Trust & Safety implemented, unit-tested, live-validated, documented, committed
22 | Done | Phase 22: Billing / Entitlements implemented, unit-tested, live-validated, documented, committed
23 | Done | Phase 23: Analytics implemented, unit-tested, live-validated, documented, committed
24 | Done | Phase 24: AI Gateway implemented, unit-tested, live-validated, documented, committed
1 | Done | Repo health baseline (make doctor / validate-all / go test / go build) run and passed
2 | Done | Environment / ApplicationVersion / ApplicationConfiguration | Deferred - no consumer needs them yet, documented as intentional in applications/README.md
5 | Done | Separate Session table | Deferred - Device.SessionStatus covers today's single-session-per-device need, documented in devices/README.md
9 | Pending | UserPreferences (named in Phase 4, no fields ever specified) | Deferred to Phase 12+; notification preferences shipped, a generic preferences bag did not
9 | Pending | apps/mobile test/ directory (make flutter-test currently fails) | Known gap since Phase 9's audit, not yet picked up
9 | Pending | apps/admin next@15 / sharp transitive advisories | Fix is a Next.js major-version bump - separate, reviewable change
20 | Done | Privacy: consent (append-only history)
20 | Done | Privacy: user data export (ExportUserData registry - users/devices/files/audit)
20 | Done | Privacy: user deletion (DeleteUserData registry - users/devices/files; audit deliberately excluded)
20 | Done | Privacy: retention policy (declared, not scheduled - same documented gap as Phase 13's PurgeExpired)
20 | Done | Privacy: privacy preferences
20 | Done | Privacy: coordinate deletion through workflows/events - core-api's own embedded Temporal worker
20 | Pending | Privacy: notifications module as an Export/Delete participant | Deliberately deferred to prove the registry makes this a 2-line addition later, not a framework change
20 | Pending | Privacy: relationships/groups/messaging as participants | Deferred - shared multi-user data needs a redaction strategy this phase's per-user-in-isolation registry doesn't fit
21 | Done | Trust & Safety: Block | Reused Phase 8's relationships (Status='blocked'), deliberately not duplicated
21 | Done | Trust & Safety: Mute
21 | Done | Trust & Safety: Report -> ModerationCase (deduplicated via partial unique index)
21 | Done | Trust & Safety: Suspension
21 | Done | Trust & Safety: Ban
21 | Done | Trust & Safety: Appeal (approving lifts the target restriction)
21 | Done | Trust & Safety: rate limiting (new platformkit/ratelimit, Valkey-backed)
21 | Done | Trust & Safety: spam protection (5 reports/hour per reporter)
21 | Done | Trust & Safety: abuse signals (critical severity auto-opens a case)
21 | Done | Trust & Safety: pluggable product-specific report reasons (free-form Reason field)
21 | Done | Trust & Safety: Suspension/Ban actually restrict access (new requireActive middleware, one entry point)
21 | Pending | Trust & Safety: WebSocket disconnect on suspension/ban | Deferred - only HTTP access is gated; an existing realtime-gateway connection isn't forcibly closed
21 | Pending | Trust & Safety: aggregating lower-severity signals over a time window | Deferred - a real abuse-detection engine is out of this phase's scope; only single-critical-signal escalation is implemented
22 | Done | Billing: Payment model (provider-specific transaction record)
22 | Done | Billing: Entitlement model (platform-facing truth, kept separate from Payment)
22 | Done | Billing: provider abstraction (PaymentProvider interface + registry, implemented first)
22 | Done | Billing: Stripe adapter | Real HMAC-SHA256 webhook signature verification, live-validated without a Stripe account via self-signed test payloads
22 | Pending | Billing: Apple IAP adapter | Deferred - needs real App Store Server API credentials this environment doesn't have
22 | Pending | Billing: Google Play adapter | Deferred - needs real Play Developer API credentials this environment doesn't have
23 | Done | Analytics: generic event envelope (event_name/user_id/anonymous_id/app_id/session_id/timestamp/properties/context)
23 | Done | Analytics: keep operational DBs out of the analytics path (analytics_events is a landing buffer, never queried for analytics)
23 | Done | Analytics: pipeline foundation for ClickHouse/warehouse/data lake (worker batches NDJSON into MinIO/S3)
23 | Pending | Analytics: an actual ClickHouse/warehouse/data-lake query layer | Out of scope - this phase builds the landing pipeline only; no real destination system exists in this environment to integrate against honestly
24 | Done | AI Gateway: provider-neutral interface (Provider: Name + Complete)
24 | Done | AI Gateway: local models / Ollama adapter | Real local inference via a new Ollama container, auto-pulled model, no vendor API key - the one live-testable provider
24 | Pending | AI Gateway: OpenAI adapter | Deferred - no real API key in this environment to validate against honestly
24 | Pending | AI Gateway: Anthropic adapter | Deferred - no real API key in this environment to validate against honestly
24 | Pending | AI Gateway: Google adapter | Deferred - no real API key in this environment to validate against honestly
24 | Done | AI Gateway: model routing (product-facing ModelAlias, never a vendor model name)
24 | Done | AI Gateway: quotas (ratelimit.Limiter reused a third time, 60/min/caller)
24 | Done | AI Gateway: token usage tracking
24 | Done | AI Gateway: cost tracking (real per-route price table; Ollama honestly priced at 0)
24 | Done | AI Gateway: audit integration (new AIGatewayAuditRecorder, a genuine audit.Record per call)
24 | Done | AI Gateway: prompt/version metadata (free-form PromptKey/PromptVersion)
24 | Done | AI Gateway: timeouts (context.WithTimeout per provider call)
24 | Done | AI Gateway: fallback (ordered provider/model chain, first success wins)
24 | Pending | AI Gateway: live token-quantity quota (as opposed to today's call-count quota) | Deferred - Repository already has the data (Completion.TotalTokens); not wired as a live gate yet
25 | Pending | Admin Portal: control-plane UI in apps/admin
25 | Pending | Admin Portal: visibility: Applications
25 | Pending | Admin Portal: visibility: Users/Sessions/Devices
25 | Pending | Admin Portal: visibility: Roles/Permissions
25 | Pending | Admin Portal: visibility: Tenants/Relationships
25 | Pending | Admin Portal: visibility: Messages/Notifications
25 | Pending | Admin Portal: visibility: Files/Jobs
25 | Pending | Admin Portal: visibility: Feature flags/Configuration
25 | Pending | Admin Portal: visibility: Moderation/Audit
25 | Pending | Admin Portal: visibility: System health/Deployments
25 | Pending | Admin Portal: must go through service APIs, never direct DB queries
26 | Pending | Backstage: integrate Backstage as developer portal
26 | Pending | Backstage: per-module metadata: name/description/owner/lifecycle
26 | Pending | Backstage: per-module metadata: repository/documentation/dependencies
26 | Pending | Backstage: per-module metadata: APIs/events/DB ownership/dashboards/runbooks
27 | Pending | SDKs: Flutter SDK
27 | Pending | SDKs: TypeScript SDK
27 | Pending | SDKs: Go SDK
27 | Pending | SDKs: auth + token refresh in each SDK
27 | Pending | SDKs: pagination + safe retries
27 | Pending | SDKs: realtime connection helper
27 | Pending | SDKs: correlation ID propagation
27 | Pending | SDKs: device registration helper
28 | Pending | Observability Completion: structured logs everywhere
28 | Pending | Observability Completion: metrics everywhere
28 | Pending | Observability Completion: distributed traces everywhere
28 | Pending | Observability Completion: health checks everywhere
28 | Pending | Observability Completion: dashboard: API latency
28 | Pending | Observability Completion: dashboard: error rate
28 | Pending | Observability Completion: dashboard: requests/sec
28 | Pending | Observability Completion: dashboard: DB connections
28 | Pending | Observability Completion: dashboard: Kafka lag
28 | Pending | Observability Completion: dashboard: WebSocket connections
28 | Pending | Observability Completion: dashboard: Redis latency
28 | Pending | Observability Completion: dashboard: notification failures
28 | Pending | Observability Completion: dashboard: background job failures
28 | Pending | Observability Completion: alerting rules
29 | Pending | Platform Control Plane: one view: applications/services/versions
29 | Pending | Platform Control Plane: one view: environments/dependencies/deployments
29 | Pending | Platform Control Plane: one view: DB ownership/events/API contracts
29 | Pending | Platform Control Plane: one view: health/alerts/recent changes
30 | Pending | AI Development Context: every module: README
30 | Pending | AI Development Context: every module: ownership metadata
30 | Pending | AI Development Context: every module: dependencies
30 | Pending | AI Development Context: every module: API contract
30 | Pending | AI Development Context: every module: event contracts
30 | Pending | AI Development Context: every module: DB ownership

## Modules
Module | Service | Responsibility | Storage | Access model | Introduced
applications | core-api | Application CRUD, the platform's own top-level tenant-of-tenants concept | applications | Open (read) / unauthenticated create in this phase's scope | Phase 2
identity | core-api | Auth provider abstraction (Keycloak today), token validation, identity<->user linkage | identities | Bearer token required for /me | Phase 3
users | core-api | Platform person/account, profile, soft-delete lifecycle | users | Self, or self-or-platform.admin for cross-user GET | Phase 4
devices | core-api | Per-user device + push-token registry, revoke/reactivate | devices | Self only | Phase 5
authz | core-api | Can(subject, action, resource) - RBAC + OpenFGA ReBAC, the one authorization entry point | user_roles + OpenFGA store | Self-service (HasRole) / role changes are the caller's own privileged action | Phase 6
tenants | core-api | Tenant + Membership (owner/admin/member), scoped to an Application | tenants, tenant_memberships | Member-only reads, owner/admin-only writes | Phase 7
relationships | core-api | Generic relationship graph: request/accept/decline/remove/block | relationships | Participant-only | Phase 8
groups | core-api | Generic Group/GroupMember, free-form roles, IsManager structural bit | groups, group_members | Member-only reads, manager-only writes | Phase 9
realtime-gateway (service) | realtime-gateway | WebSocket connections, channels, presence, direct/broadcast delivery | none (Redis/Valkey only) | Bearer token required at handshake | Phase 10
messaging | core-api | Conversation/Message/Delivery/ReadState/Reaction/Attachment | conversations, conversation_members, messages, message_* | Conversation-member-only | Phase 11
notifications | core-api | Notification/Template/Preference/Delivery across 5 channels | notifications, notification_requests, notification_preferences | Self-or-platform.admin to send; templates are platform.admin-only | Phase 12
files | core-api | Presigned upload/download, ownership, retention, checksum | files | Owner-or-platform.admin, visibility-scoped downloads | Phase 13
search | core-api | SearchDocument/SearchProvider over OpenSearch | none (OpenSearch only) | Open query; admin-only manual index/delete | Phase 14
worker: indexer | worker | Event-driven OpenSearch indexer, polls outbox_events | reads outbox_events | n/a (background) | Phase 14
jobs | core-api | Job/JobStatus/JobAttempt - immediate/scheduled/delayed/recurring/retry/dead-letter | jobs, job_attempts | Owner-or-platform.admin | Phase 15
worker: jobrunner | worker | Claims and executes due jobs (Echo, Webhook handlers) | reads/writes jobs, job_attempts | n/a (background) | Phase 15
workflows | core-api | Core Workflow API/SDK over Temporal (Start/Describe/Signal only) | workflow_runs (ownership only - state lives in Temporal) | Owner-or-platform.admin | Phase 16
worker: workflows | worker | ApprovalWorkflow, PingWebhookWorkflow (Temporal worker) | none (Temporal-native state) | n/a (background) | Phase 16
features | core-api | Feature/FeatureRule/FeatureEvaluation, deterministic percentage rollout | features, feature_rules | Open evaluate; platform.admin-only manage | Phase 17
remoteconfig | core-api | Typed KV config store, full audit trail per change | config_entries, config_changes | Open read; platform.admin-only write/history | Phase 18
audit | core-api | Central, immutable audit trail (API-omission + DB trigger enforced) | audit_events | Open to record; platform.admin-only to read | Phase 19
privacy | core-api | Consent, preferences, retention policy, cross-module export/delete via a registry | privacy_consents, privacy_preferences, retention_policies, data_export_requests, data_deletion_requests | Self for own data; platform.admin for retention policies | Phase 20
privacy: embedded Temporal worker | core-api | Runs privacy's own export/deletion workflows in-process (task queue privacy-tasks) | none (Temporal-native state) | n/a (background, inside core-api's own process) | Phase 20
trustsafety | core-api | Mute/Report/ModerationCase/Suspension/Ban/Appeal/AbuseSignal - Block reuses Phase 8's relationships | mutes, moderation_cases, reports, suspensions, bans, appeals, abuse_signals | Self for own mutes/appeals; moderator-or-admin for case/suspension/ban management | Phase 21
billing | core-api | Entitlement (platform truth) kept separate from Payment (provider transaction record); PaymentProvider abstraction + registry | entitlements, payments | Self for own entitlements/payments; platform.admin for manual grants | Phase 22
billing/stripe | core-api | Real Stripe webhook HMAC-SHA256 signature verification - the one live-testable PaymentProvider this phase ships | none (stateless verification) | n/a (provider-signature-authenticated, not a Bearer route) | Phase 22
analytics | core-api | Generic event envelope ingestion; analytics_events is a landing buffer, never a query surface | analytics_events | Open (IP-rate-limited) to track; platform.admin-only debug listing | Phase 23
worker: analyticspipeline | worker | Claims unflushed events, batches as NDJSON, writes to MinIO/S3 - the ClickHouse/warehouse/data-lake landing pattern | reads/writes analytics_events; writes MinIO/S3 | n/a (background) | Phase 23
aigateway | core-api | Provider-neutral completions API - model routing, quotas, cost tracking, audit, timeouts, fallback | ai_completions | Self for own usage; open (quota-limited) to complete | Phase 24
aigateway/ollama | core-api | Real local-inference Provider adapter - the one live-testable Provider this phase ships | none (stateless HTTP client to a real Ollama container) | n/a (internal provider adapter, not a route) | Phase 24

## API Endpoints
Method | Path | Module | Auth | Notes
GET | /livez | platform | Open | process alive
GET | /readyz | platform | Open | dependencies ready
GET | /healthz | platform | Open | aggregated health
GET | /v1/platform | platform | Open | platform name/env/version
POST | /v1/apps | applications | Open (this phase's scope)
GET | /v1/apps | applications | Open | cursor-paginated list
GET | /v1/apps/{id} | applications | Open
PATCH | /v1/apps/{id} | applications | Open (this phase's scope)
GET | /v1/identity/me | identity | Authenticated | resolves the caller's Identity
GET | /v1/users/me | users | Authenticated (self)
PATCH | /v1/users/me | users | Authenticated (self)
GET | /v1/users/{id} | users | Self or platform.admin
GET | /v1/users/me/devices | devices | Authenticated (self)
POST | /v1/users/me/devices | devices | Authenticated (self) | register/upsert
DELETE | /v1/users/me/devices/{id} | devices | Authenticated (self) | soft-revoke
GET | /v1/tenants | tenants | Authenticated | scoped to caller's own tenants
POST | /v1/tenants | tenants | Authenticated | creator becomes owner
GET | /v1/tenants/{id} | tenants | Member
PATCH | /v1/tenants/{id} | tenants | Owner or admin
GET | /v1/tenants/{id}/members | tenants | Member
POST | /v1/tenants/{id}/members | tenants | Owner or admin
DELETE | /v1/tenants/{id}/members/{userId} | tenants | Owner/admin, or self (leave)
GET | /v1/relationships | relationships | Participant
GET | /v1/relationships/{id} | relationships | Participant
POST | /v1/relationships | relationships | Authenticated | request
POST | /v1/relationships/block | relationships | Authenticated
POST | /v1/relationships/{id}/accept | relationships | Target only
POST | /v1/relationships/{id}/decline | relationships | Target only
DELETE | /v1/relationships/{id} | relationships | Participant | remove/unfriend
GET | /v1/groups | groups | Member
POST | /v1/groups | groups | Authenticated | creator becomes manager
GET | /v1/groups/{id} | groups | Member
PATCH | /v1/groups/{id} | groups | Manager
GET | /v1/groups/{id}/members | groups | Member
POST | /v1/groups/{id}/members | groups | Manager
PATCH | /v1/groups/{id}/members/{userId} | groups | Manager | promote/demote IsManager
DELETE | /v1/groups/{id}/members/{userId} | groups | Manager, or self (leave)
WS | /ws (realtime-gateway) | realtime-gateway | Bearer token at handshake | subscribe/publish/broadcast/direct message
GET | /v1/conversations | messaging | Member
POST | /v1/conversations | messaging | Authenticated | direct convos dedup automatically
GET | /v1/conversations/{id} | messaging | Member
GET | /v1/conversations/{id}/members | messaging | Member
POST | /v1/conversations/{id}/members | messaging | Member (group only)
DELETE | /v1/conversations/{id}/members/{userId} | messaging | Self only (leave)
GET | /v1/conversations/{id}/messages | messaging | Member | cursor pagination
POST | /v1/conversations/{id}/messages | messaging | Member | pushes over realtime too
GET | /v1/conversations/{id}/messages/{messageId} | messaging | Member
POST | /v1/conversations/{id}/messages/{messageId}/delivered | messaging | Member | idempotent ack
GET | /v1/conversations/{id}/messages/{messageId}/reactions | messaging | Member
POST | /v1/conversations/{id}/messages/{messageId}/reactions | messaging | Member | idempotent add
DELETE | /v1/conversations/{id}/messages/{messageId}/reactions/{type} | messaging | Member
GET | /v1/conversations/{id}/read/{userId} | messaging | Member
PUT | /v1/conversations/{id}/read | messaging | Member
GET | /v1/notifications | notifications | Authenticated (self)
POST | /v1/notifications | notifications | Self or platform.admin | send
GET | /v1/notifications/{id} | notifications | Self or platform.admin
GET | /v1/notifications/{id}/deliveries | notifications | Self or platform.admin
POST | /v1/notifications/{id}/deliveries/{deliveryId}/retry | notifications | Self or platform.admin
GET | /v1/notification-preferences | notifications | Authenticated (self)
PUT | /v1/notification-preferences | notifications | Authenticated (self) | category opt-outs
GET | /v1/notification-preferences/quiet-hours | notifications | Authenticated (self)
PUT | /v1/notification-preferences/quiet-hours | notifications | Authenticated (self)
POST | /v1/notification-templates | notifications | platform.admin
GET | /v1/notification-templates/{appId}/{key} | notifications | platform.admin
PATCH | /v1/notification-templates/{appId}/{key} | notifications | platform.admin
GET | /v1/files | files | Owner or platform.admin
POST | /v1/files | files | Authenticated | requests a presigned upload URL
POST | /v1/files/{id}/confirm | files | Owner | verifies real size + MD5 checksum
GET | /v1/files/{id} | files | Owner, or public if visibility allows
GET | /v1/files/{id}/download | files | Owner, or public if visibility allows | presigned GET
DELETE | /v1/files/{id} | files | Owner or platform.admin | also deletes from storage
POST | /v1/files/purge-expired | files | platform.admin
GET | /v1/search | search | Open
POST | /v1/search/index | search | platform.admin | manual index (normally event-driven)
DELETE | /v1/search/index/{type}/{id} | search | platform.admin
GET | /v1/jobs | jobs | Owner or platform.admin
POST | /v1/jobs | jobs | Authenticated | enqueue only - never runs inline
GET | /v1/jobs/{id} | jobs | Owner or platform.admin
GET | /v1/jobs/{id}/attempts | jobs | Owner or platform.admin
POST | /v1/workflows | workflows | Authenticated | starts a Temporal workflow
GET | /v1/workflows/{id} | workflows | Owner or platform.admin | live-queried from Temporal
POST | /v1/workflows/{id}/signal | workflows | Owner or platform.admin
GET | /v1/features | features | platform.admin
POST | /v1/features | features | platform.admin
GET | /v1/features/{appId}/{key} | features | platform.admin
PATCH | /v1/features/{appId}/{key} | features | platform.admin | kill switch etc
POST | /v1/features/{appId}/{key}/evaluate | features | Open | isEnabled(feature, context)
GET | /v1/features/{appId}/{key}/rules | features | platform.admin
POST | /v1/features/{appId}/{key}/rules | features | platform.admin
PATCH | /v1/features/{appId}/{key}/rules/{ruleId} | features | platform.admin
DELETE | /v1/features/{appId}/{key}/rules/{ruleId} | features | platform.admin
GET | /v1/config | remoteconfig | Open | list entries
GET | /v1/config/{appId}/{environment}/{key} | remoteconfig | Open
PUT | /v1/config/{appId}/{environment}/{key} | remoteconfig | platform.admin | writes an audited Change row
DELETE | /v1/config/{appId}/{environment}/{key} | remoteconfig | platform.admin
GET | /v1/config/{appId}/{environment}/{key}/history | remoteconfig | platform.admin
POST | /v1/audit | audit | Authenticated (actor forced server-side)
GET | /v1/audit | audit | platform.admin
GET | /v1/audit/{id} | audit | platform.admin
POST | /v1/privacy/consent | privacy | Authenticated (self) | append-only history
GET | /v1/privacy/consent | privacy | Authenticated (self)
GET | /v1/privacy/preferences | privacy | Authenticated (self)
PUT | /v1/privacy/preferences | privacy | Authenticated (self)
POST | /v1/privacy/retention-policies | privacy | platform.admin
GET | /v1/privacy/retention-policies | privacy | platform.admin
POST | /v1/privacy/export | privacy | Authenticated (self) | starts a Temporal workflow
GET | /v1/privacy/export/{id} | privacy | Self or platform.admin | status is read from Postgres, not Temporal
GET | /v1/privacy/export/{id}/download | privacy | Self or platform.admin | presigned MinIO/S3 GET
POST | /v1/privacy/delete | privacy | Authenticated (self) | starts a Temporal workflow
GET | /v1/privacy/delete/{id} | privacy | Self or platform.admin | a self-deleted user must use an admin to check this
POST | /v1/trustsafety/mutes | trustsafety | Authenticated (self) | one-directional, silent
GET | /v1/trustsafety/mutes | trustsafety | Authenticated (self) | exempt from requireActive - always reachable
DELETE | /v1/trustsafety/mutes/{userId} | trustsafety | Authenticated (self)
POST | /v1/trustsafety/reports | trustsafety | Authenticated (self) | rate-limited 5/hour; dedupes onto one case
GET | /v1/trustsafety/reports/{id} | trustsafety | Reporter or moderator/admin
GET | /v1/trustsafety/cases | trustsafety | Moderator or platform.admin | ?status=
GET | /v1/trustsafety/cases/{id} | trustsafety | Moderator or platform.admin
GET | /v1/trustsafety/cases/{id}/reports | trustsafety | Moderator or platform.admin
PATCH | /v1/trustsafety/cases/{id}/assign | trustsafety | Moderator or platform.admin
PATCH | /v1/trustsafety/cases/{id} | trustsafety | Moderator or platform.admin | resolve/dismiss
POST | /v1/trustsafety/suspensions | trustsafety | Moderator or platform.admin | temporary, EndsAt required
GET | /v1/trustsafety/suspensions | trustsafety | Self or moderator/admin | ?userId=
POST | /v1/trustsafety/suspensions/{id}/lift | trustsafety | Moderator or platform.admin
POST | /v1/trustsafety/bans | trustsafety | Moderator or platform.admin | permanent until lifted
GET | /v1/trustsafety/bans | trustsafety | Self or moderator/admin | ?userId=
POST | /v1/trustsafety/bans/{id}/lift | trustsafety | Moderator or platform.admin
POST | /v1/trustsafety/appeals | trustsafety | Authenticated (self, must own target) | exempt from requireActive - always reachable
GET | /v1/trustsafety/appeals | trustsafety | Self or moderator/admin | exempt from requireActive - always reachable
POST | /v1/trustsafety/appeals/{id}/review | trustsafety | Moderator or platform.admin | approving lifts the target restriction
POST | /v1/trustsafety/signals | trustsafety | Authenticated | critical severity auto-opens a case
GET | /v1/trustsafety/signals | trustsafety | Moderator or platform.admin | ?resourceType=&resourceId=
GET | /v1/billing/entitlements | billing | Self or platform.admin | ?userId=
GET | /v1/billing/entitlements/check/{key} | billing | Authenticated (self) | the literal 'do I have entitlement X' check
POST | /v1/billing/entitlements | billing | platform.admin | manual grant; source always "manual:<adminId>"
POST | /v1/billing/entitlements/{id}/revoke | billing | platform.admin
GET | /v1/billing/payments | billing | Self or platform.admin | ?userId=
POST | /v1/billing/webhooks/{provider} | billing | Provider webhook signature (no Bearer token) | the one route on this platform with no requireUser/requireActive
POST | /v1/analytics/events | analytics | Open (IP-rate-limited, no Bearer token) | the platform's one deliberately unauthenticated write endpoint
GET | /v1/analytics/events | analytics | platform.admin | operational debug view only, not for analytical queries
POST | /v1/ai/completions | aigateway | Authenticated (quota-limited) | real local inference via Ollama; never call a vendor model name directly
GET | /v1/ai/usage | aigateway | Self or platform.admin | ?userId=; tokens/cost/latency, never prompt or response text
GET | /v1/ai/models | aigateway | Authenticated | lists registered model aliases, never vendor model names

## How To Test
Step | What | Command / Where | Notes
1 | Bring up local infra | make local-up | Starts Postgres, Valkey, Keycloak, OpenFGA, MinIO, OpenSearch, Temporal, Kafka/Redpanda + the observability stack (13 containers). Idempotent, one command.
2 | Check everything is healthy | docker ps | Every container should show 'Up' (Postgres shows '(healthy)'). Re-run make local-up if anything is missing - Keycloak/OpenFGA have no persistent volume, so realm/store data is re-imported on every restart.
3 | Build the services | make build | Compiles core-api, realtime-gateway, worker, and platformkit. Should exit 0 with no output.
4 | Run the test suite | make test | Runs every module's unit tests against in-memory fakes. Should be all 'ok'.
5 | Start core-api | set -a && source .env && set +a && go run ./backend/core-api/cmd/server | Listens on :8080 (see Infra sheet). Watch its stdout for structured JSON logs.
6 | Start realtime-gateway (optional) | set -a && source .env && set +a && go run ./backend/realtime-gateway/cmd/server | Listens on :8090. Only needed to test WebSocket/presence features.
7 | Start worker (optional) | set -a && source .env && set +a && go run ./backend/worker/cmd/worker | Runs the job runner, search indexer, and Temporal workflow worker. Only needed to test jobs/search/workflows end to end.
8 | Confirm the API is up | curl -s http://localhost:8080/healthz | Should return {"status":"ok",...} with every dependency 'ok': true.
9 | Mint a real login token | curl -s -X POST http://localhost:8081/realms/core/protocol/openid-connect/token -d grant_type=password -d client_id=core-platform -d username=demo -d password=demo ¦ python3 -c "import sys,json;print(json.load(sys.stdin)['access_token'])" | The realm ships one seeded user, 'demo' / 'demo'. Save the output as $TOKEN - it's a real JWT good for 300 seconds.
10 | Call an authenticated endpoint | curl -s http://localhost:8080/v1/users/me -H "Authorization: Bearer $TOKEN" | First call auto-provisions a platform User linked to the Keycloak identity. Re-run it - you get back the same user.
11 | Create a second, non-admin test user | Use Keycloak's Admin API (admin/admin against the master realm) to POST a user to /admin/realms/core/users - see the Audit phase's live validation for the exact curl sequence. | Needed for anything that checks cross-user permissions (403-for-a-stranger tests).
12 | Grant platform.admin to a user | There is no HTTP route for this by design (it's a privileged, rarely-needed action) - write a small throwaway Go program under backend/core-api/cmd/<name>/main.go that constructs authz.Service the same way cmd/server/main.go does and calls AssignRole, then delete it. | This is the same pattern used to verify every admin-gated module during development - see any phase's entry in VALIDATION.md for a worked example.
13 | Exercise a module end-to-end | e.g. POST /v1/apps, then GET /v1/apps, then GET /v1/apps/{id} with the returned id | Pick any row from the 'API Endpoints' sheet and try it - every route takes/returns plain JSON. Look at each module's own README.md (backend/core-api/internal/<module>/README.md) for the exact request/response shapes and the scoping decisions behind them.
14 | Watch a WebSocket live | wscat -c "ws://localhost:8090/ws?access_token=$TOKEN" (or any RFC6455 client) | You should receive a {"type":"connected",...} frame immediately. Subscribe to a channel, then publish from a second connection to see fan-out.
15 | Watch the database directly | docker exec -it docker-postgres-1 psql -U core -d core | Useful for sanity-checking: SELECT * FROM outbox_events ORDER BY id DESC LIMIT 20; or SELECT * FROM audit_events ORDER BY occurred_at DESC LIMIT 20;
16 | Read the validation history | VALIDATION.md (repo root) | Every phase's actual live-validation pass is written up there in detail - exact curl sequences, real bugs found and fixed, and what was deliberately left out of scope.
17 | Run the smoke test | make smoke | A scripted end-to-end pass (scripts/smoke.sh) against the real running services - the fastest single command to confirm the whole stack still works after a change.
18 | Skip the curl entirely | Open this dashboard's API Console tab | Pick an endpoint, fetch a token via the built-in Keycloak password-grant form (or paste one you already have), and send the request - the real response comes back right in the page. core-api's CORS middleware (internal/api/cors.go) is what makes this possible; it must be running a build from Phase 21 or later.

## Infra & Credentials
Service | Type | Address | Purpose | Local credentials
core-api | Go service | http://localhost:8080 | The main platform API - almost every module in this workbook lives here. | n/a
realtime-gateway | Go service | ws://localhost:8090 | WebSocket connections, presence, channel fan-out. | n/a
worker | Go service | http://localhost:8091 (health only) | Background job runner, search indexer, Temporal workflow worker, analytics NDJSON pipeline. | n/a
Postgres | Docker container | localhost:5432 | System of record for every domain module. | core / core, db 'core'
Valkey (Redis-compatible) | Docker container | localhost:6379 | Realtime pub/sub fan-out, presence (TTL-based). | no auth locally
Keycloak | Docker container | http://localhost:8081 | Identity provider. Realm 'core' is re-imported on every restart (no persistent volume). | admin/admin (master realm); demo/demo (core realm, seeded user)
OpenFGA | Docker container | http://localhost:8082 | Fine-grained ReBAC engine behind authz.Service.Can. In-memory store, self-heals its store/model on every restart. | no auth locally
MinIO (S3-compatible) | Docker container | http://localhost:9000 | Object storage backing the files module. | minio / minio123, bucket 'core-platform'
OpenSearch | Docker container | http://localhost:9200 | Backs the search module, indexed by worker's indexer. | no auth locally
Temporal | Docker container | localhost:7233 | Durable workflow execution engine behind the workflows module. | no auth locally
Kafka / Redpanda | Docker container | localhost:9092 | Health-checked today; no producer wired yet (outbox-to-Kafka relay is a documented future gap). | no auth locally
Ollama | Docker container | http://localhost:11434 | Real local LLM inference behind the AI Gateway - model qwen2.5:0.5b auto-pulled on every start, no vendor API key needed. | no auth locally
OTel Collector / Tempo / Prometheus / Grafana / Loki | Docker containers | see infra/docker/docker-compose.yml | Full observability stack - traces, metrics, logs, dashboards. | no auth locally